## Task Tracker
MAY 2026 — PRODUCT DEPARTMENT ¦ MONTHLY TASK CLOSING REPORT
Reporting Period: May 1 – May 30, 2026 ¦ Department: Product ¦
# | Task / Deliverable | Task Owner | Priority | Start Date | End Date | Status | Notes / Outcome
1 | XYZ Task | Product Team | Critical | 01-May-26 | - | In Progress | ASC provided in PRE, and Finance-side validation is currently pending. Upon successful conclusion, this will be moved to Staging for further verification.
2 | XYZ Task | Product Team | High | 01-May-26 | 2026-05-13 | Completed | Functionality is working as expected, with Compliance Testing completed successfully and testing evidence attached on ticket
3 | XYZ Task | Product Team | High | 2026-05-18 | 2026-05-20 | Completed | Event mapping for Consumer Onboarding has been completed with 198 analytics events, including relevant event sources, tracking properties, and capture parameters for comprehensive product analytics implementation.
4 | XYZ Task | Product Team | Medium | 2026-04-24 | 2026-05-22 | Completed | Decision Tree testing for Consumer Onboarding was conducted with Compliance, Product, and Operations teams. Findings were validated with ASC, and improvement items were added to the June sprint backlog.
5 | XYZ Task | Product Team | Critical | 2026-04-29 | 20-May-26 | Completed | Virtual Card Issuance work page is in progress as per departmental BRD; requirements remain pending due to awaiting compliance information from Stripe. Design has been completed, and in-app notifications along with T&Cs have been finalized.
6 | XYZ Task | Product Team | High | 2026-05-02 | 22-May-26 | Completed | Card Expiry Flow for Consumer has been defined with automatic expiry detection and user prompt for reordering a new card. The work package has been finalized and included in the June sprint backlog.
7 | XYZ Task | Product Team | Critical | 2026-05-08 | 2026-05-21 | Completed | Stripe iOS requirements, including flow videos and the Apple checklist, have been compiled and submitted for review.
8 | XYZ Task | Product Team | Medium | 2026-05-10 | 2026-05-22 | Completed | Backlog groomed and prioritised for June cycle.
9 | XYZ Task | Product Team | High | 2026-05-22 | 2026-05-22 | Completed | Product acceptance testing complete and feedback shared with ASC
10 | XYZ Task | Product Team | High | 2026-05-15 | 2026-05-15 | Completed | Rollout complete. Live monitoring in place for edge cases.
11 | XYZ Task | Product Team | Critical | 01-May-26 | 30-May-26 | In Progress | 4 production issues identified; 2 resolved; 2 in progress.
12 | XYZ Task | Product Team | Medium | 2026-05-10 | 2026-05-21 | Completed | Research report compiled. Compertitors design options received from Design Team.
TOTALS |  |  | 12 |  |  | Completed: 10 ¦ In Progress: 2 ¦ On Hold: 0 ¦ Pending: 0 ¦ Cancelled: 0