## 📊 Dashboard
✅ UMAIR TASK LIST DASHBOARD
| 📋 TOTAL TASKS |  | 🔄 IN PROGRESS |  | ✅ COMPLETED | 🔥 OVERDUE
| 37 |  | 4 |  | 29 | 5
COMPLETION RATE
76.32%
PRIORITY BREAKDOWN
| Priority | Count |  | % of Total
| 🔴 Critical | 6 |  | 16.22%
| 🟠 High | 13 |  | 35.14%
| 🟡 Medium | 14 |  | 37.84%
| 🟢 Low | 5 |  | 13.51%

## 📈 Analytics
📈 TASK ANALYTICS
STATUS SUMMARY
Status | Count | Percentage
Completed | 29 | 76.32%
In Progress | 4 | 10.53%
Not Started | 4 | 10.53%
On Hold | 1 | 2.632%
Cancelled | 0 | 0%
PRIORITY BREAKDOWN
Priority | Count | Percentage
Critical | 6 | 15.79%
High | 13 | 34.21%
Medium | 14 | 36.84%
Low | 5 | 13.16%

## 📋 Task List
📋 TASK LIST
# | Task ID | Task Name | Description | Category | Assigned To | Due Date | Date Started | Status | Priority | Progress % | Notes
1 | TSK-001 | XYZ Task | Test the Back Office functionality for requests initiated from the front end, including cancellations and other workflows. | Testing | Umair Ahmed | 2026-02-13 |  | Completed | High | 100
2 | TSK-002 | XYZ Task | Conduct end-to-end testing on the front-end application, covering standard use cases, edge cases, and full functionality verification. | Testing | Umair Ahmed | 2026-02-13 |  | Completed | High | 100
3 | TSK-003 | XYZ Task | Research compliance requirements, create a detailed BRD, and test backend logic and visibility in both pre-production and staging environments. | Testing | Umair Ahmed | 2026-03-27 |  | Completed | High | 100
4 | TSK-004 | XYZ Task | Investigate and resolve revenue calculation issues in Stripe and fix the transaction export functionality for Finance. | Finance | Umair Ahmed | 2026-03-11 |  | Completed | High | 100
5 | TSK-005 | XYZ Task | Provide a complete breakdown and analysis of standard and non-standard pricing models and revenue-sharing structures. | Finance | Umair Ahmed | 2026-03-18 |  | Completed | High | 100
6 | TSK-006 | XYZ Task | Conduct UAT for the transition from Frame to Flow in the checkout process to ensure seamless functionality. | Testing | Umair Ahmed | 2026-02-26 |  | In Progress | Medium | 70 | Pending on ASC
7 | TSK-007 | XYZ Task | Review the updated business account onboarding process and provide detailed feedback for improvements. | Product | Umair Ahmed | 2026-04-03 |  | Completed | Medium | 60 | Feedback prodiveded done form my side
8 | TSK-008 | XYZ Task | Investigate the bank incident causing a 400 error, conduct root cause analysis, and document findings for resolution. | Other | Umair Ahmed | 2026-03-23 |  | Completed | Critical | 100
9 | TSK-009 | XYZ Task | Conduct comprehensive research and competitor analysis to design and validate a tiered pricing model. | Research | Umair Ahmed | 2026-04-12 |  | Completed | High | 100
10 | TSK-010 | XYZ Task | Research UK lenders and BNPL providers that offer Shariah-compliant financing solutions. | Research | Umair Ahmed | 2026-03-20 |  | Completed | Medium | 100
11 | TSK-011 | XYZ Task | Create multiple concept papers outlining strategic product initiatives and future roadmap items. | Documentation | Umair Ahmed | 2026-03-12 |  | In Progress | Low | 70
12 | TSK-012 | XYZ Task | Develop a concept paper allowing users to lock exchange rates for up to two years. | Documentation | Umair Ahmed | 2026-03-27 |  | Completed | Low | 100
13 | TSK-013 | XYZ Task | Develop a concept for merchants or businesses to accept card payments via NFC-enabled devices. | Documentation | Umair Ahmed | 2026-03-18 |  | Completed | Medium | 100
14 | TSK-014 | XYZ Task | Design a concept allowing businesses to pay invoices internationally with ease. | Documentation | Umair Ahmed | 2026-03-15 |  | Completed | Medium | 100
15 | TSK-015 | XYZ Task | Create a detailed concept for introducing tiered pricing based on customer segmentation and personalization. | Documentation | Umair Ahmed | 2026-04-27 |  | Completed | Medium | 100
16 | TSK-016 | XYZ Task | Prepare a TAM, SAM, and SOM analysis for open banking and other relevant services, dependent on data availability. | Other | Umair Ahmed | 2026-03-20 |  | On Hold | High | 20
17 | TSK-017 | XYZ Task | Create a complete BRD and prototype for the business account dashboard, including feature requirements and UX flows. | Product | Umair Ahmed | 2026-03-16 |  | Completed | Critical | 100
18 | TSK-018 | XYZ Task | Draft a comprehensive paper summarizing goals, priorities, and initiatives for Q1 to share with the PMO. | Documentation | Umair Ahmed | 2026-03-27 |  | Completed | Medium | 100
19 | TSK-019 | XYZ Task | Develop a document outlining the enable/disable functionality of individual features per user. | Documentation | Umair Ahmed | 2026-03-11 |  | Completed | Critical | 100
20 | TSK-020 | XYZ Task | Analyze the transaction page for missing elements and document improvements for the next development sprint. | Operations | Umair Ahmed | 2026-03-18 |  | Completed | High | 100
21 | TSK-021 | XYZ Task | Conduct end-to-end testing for inward cancellation; ensure refunds are automatically processed to the sender’s bank. | Testing | Umair Ahmed | 2026-03-14 |  | Completed | Critical | 100
22 | TSK-022 | XYZ Task | Update onboarding to include a single trading address point, discuss with compliance, and implement in the revamped workflow. | Testing | Umair Ahmed | 2026-04-03 |  | Completed | Medium | 100
23 | TSK-023 | XYZ Task | Perform full end-to-end testing of Tap to Pay in the staging environment and compile a complete test report. | Testing | Umair Ahmed | 2026-03-23 |  | Completed | Critical | 100
24 | TSK-024 | XYZ Task | Develop a comprehensive BRD and rebuttal for operations, including industry research on card expiry processes. | Documentation | Umair Ahmed | 2026-04-12 |  | In Progress | High | 70
25 | TSK-025 | XYZ Task | Create detailed test cases covering all scenarios for Tap to Pay functionality. | Documentation | Umair Ahmed | 2026-03-20 |  | Completed | Medium | 100
26 | TSK-026 | XYZ Task | Propose innovative ideas for invoice and bill payment features during the session. | Product | Umair Ahmed | 2026-03-12 |  | Completed | Medium | 100
27 | TSK-027 | XYZ Task | Compile a complete report documenting issues encountered across different testing environments. | Other | Umair Ahmed | 2026-03-27 |  | Completed | Medium | 100
28 | TSK-028 | XYZ Task | Conduct research on competitor onboarding processes and compile reference videos for analysis. | Other | Umair Ahmed | 2026-03-18 |  | Completed | Medium | 100
29 | TSK-029 | XYZ Task | Test consumer card expiry workflows and ensure smooth issuance of replacement cards. | Testing | Umair Ahmed | 2026-03-15 |  | Completed | High | 100
30 | TSK-030 | XYZ Task | Develop a solution to notify customers when contactless limits are exceeded and provide chip-and-PIN fallback. | Testing | Umair Ahmed | 2026-04-27 |  | Completed | Low | 100
31 | TSK-031 | XYZ Task | Conduct R&D on Stripe card issuing, including reviewing official documentation and best practices. | Research | Umair Ahmed | 2026-04-28 |  | In Progress | High | 10
32 | TSK-032 | XYZ Task | Conduct a detailed gap analysis of existing EMI products, linked to business account ideation, identifying missing features, compliance gaps, and improvement opportunities. | Research | Umair Ahmed | N/A |  | Not Started | Low | 0
33 | TSK-033 | XYZ Task | Map all MVP events, documenting both basic flows and feature-specific workflows to ensure complete end-to-end coverage. | Other | Umair Ahmed | N/A |  | Not Started | Low | 0
34 | TSK-034 | XYZ Task | Conduct sessions with the Operations team to help them understand and navigate the Stripe dashboard effectively. | Product | Umair Ahmed | 2026-04-28 |  | Completed | Medium | 100
35 | TSK-035 | XYZ Task | Research and clarify responsibility and processes when a connected account balance goes negative. | Finance | Umair Ahmed | 2026-04-28 |  | Completed | Medium | 100
36 | TSK-036 | XYZ Task | Perform testing of Stripe functionalities in the live production environment. | Product | Umair Ahmed | 2026-04-28 |  | Completed | Critical | 100
37 | TSK-037 | XYZ Task | Verify that all emails and notifications are correctly triggered and received in the production environment. | Product | Umair Ahmed |  |  | Not Started | High | 0
38 | TSK-038 |  |  | Product | Umair Ahmed |  |  | Not Started | High | 0
39 | TSK-039
40 | TSK-040
41 | TSK-041
42 | TSK-042
43 | TSK-043
44 | TSK-044
45 | TSK-045
46 | TSK-046
47 | TSK-047
48 | TSK-048
49 | TSK-049
50 | TSK-050
51 | TSK-051
52 | TSK-052
53 | TSK-053
54 | TSK-054
55 | TSK-055
56 | TSK-056
57 | TSK-057
58 | TSK-058
59 | TSK-059
60 | TSK-060
61 | TSK-061
62 | TSK-062
63 | TSK-063
64 | TSK-064
65 | TSK-065
66 | TSK-066
67 | TSK-067
68 | TSK-068
69 | TSK-069
70 | TSK-070
71 | TSK-071
72 | TSK-072
73 | TSK-073
74 | TSK-074
75 | TSK-075
76 | TSK-076
77 | TSK-077
78 | TSK-078
79 | TSK-079
80 | TSK-080
81 | TSK-081
82 | TSK-082
83 | TSK-083
84 | TSK-084
85 | TSK-085
86 | TSK-086
87 | TSK-087
88 | TSK-088
89 | TSK-089
90 | TSK-090
91 | TSK-091
92 | TSK-092
93 | TSK-093
94 | TSK-094
95 | TSK-095
96 | TSK-096
97 | TSK-097
98 | TSK-098
99 | TSK-099
100 | TSK-100