## Full Year Roadmap
XYZ COMPANY · PRODUCT ROADMAP 2026
Q2 – Q4 2026 ¦ Consumer & Business Initiatives ¦ Confidential – Executive View
# | SWIMLANE | INITIATIVE | DESCRIPTION | PRODUCT | EST TIMELINE | STATUS | Q2 2026 |  |  | Q3 2026 |  |  | Q4 2026 |  |  | NOTES
[7 empty] | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
▶ Q1 SPILLOVERS — Completing April 2026
1 | Q1 Spillover | XYZ COMPANY | Contactless NFC acceptance | Business | 1–2 wks | In Progress | bar: Q2 2026 Apr
2 | Q1 Spillover | XYZ COMPANY | Sign-up & monthly pricing | Business | 0–1 wks | Done | bar: Q2 2026 Apr
3 | Q1 Spillover | XYZ COMPANY | Top-up & compliance visibility | Business | 1–2 wks | In Progress | bar: Q2 2026 Apr
4 | Q1 Spillover | XYZ COMPANY | B2B cross-border payments | Business | 3–4 wks | In Progress | bar: Q2 2026 Apr
▶ BUSINESS INITIATIVES
5 | Business | XYZ COMPANY | KYC/KYB flow improvement | Business | 4–6 wks | In Progress | bar: Q2 2026 May to Q2 2026 Jun
6 | Business | XYZ COMPANY | Validate BE logic front end implementation and API endpoints | Business | 4–5 wks | Planned | bar: Q3 2026 Jul
7 | Business | XYZ COMPANY | Validate BE logic front end implementation and API endpoints | Business | 4–5 wks | Planned | bar: Q2 2026 Jun
8 | Business | XYZ COMPANY | Validate user experience and customer support | Business | 4–5 wks | Planned | bar: Q3 2026 Jul
9 | Business | XYZ COMPANY | Add funds via open banking | Business | 3–5 wks | Planned | bar: Q2 2026 Jun to Q3 2026 Jul
10 | Business | XYZ COMPANY | SME invoicing creation | Business | 4–5 wks | Planned | bar: Q2 2026 Jun to Q3 2026 Jul; Q4 2026 Oct
11 | Business | XYZ COMPANY | QR-based merchant payments | Business | 2–3 wks | Planned | bar: Q2 2026 Jun to Q3 2026 Jul
12 | Business | XYZ COMPANY | Payment journey improvements | Business | 3–4 wks | Planned | bar: Q3 2026 Jul to Q3 2026 Aug
13 | Business | XYZ COMPANY | Redesign pricing structure | Business | 5–6 wks | Planned | bar: Q3 2026 Aug
14 | Business | XYZ COMPANY | Business cards (physical/virtual) | Business | 2–3 months | Planned | bar: Q2 2026 May to Q2 2026 Jun
15 | Business | XYZ COMPANY | Multi-currency wallet | Business | 2–3 months | Planned | bar: Q3 2026 Aug to Q3 2026 Sep
16 | Business | XYZ COMPANY | Analyize customer behaviour | Business | 1-3 months | Planned | bar: Q3 2026 Aug to Q3 2026 Sep
17 | Business | XYZ COMPANY | Multi-director account offering | Business | 2–3 wks | Planned | bar: Q2 2026 May to Q2 2026 Jun
18 | Business | XYZ COMPANY | Xero, QuickBooks integration | Business | 2–3 months | Planned | bar: Q4 2026 Dec
19 | Business | XYZ COMPANY | SME inventory management | Business | 2–3 months | Planned | bar: Q4 2026 Dec
20 | Business | XYZ COMPANY | Non-resident onboarding | Business | 5-6 wks | Planned | bar: Q4 2026 Nov
▶ CONSUMER INITIATIVES
21 | Consumer | XYZ COMPANY | Validate BE logic front end implementation and API endpoints | Consumer | 4–5 wks | Planned | bar: Q2 2026 Apr to Q2 2026 May
22 | Consumer | XYZ COMPANY | Validate BE logic front end implementation and API endpoints | Consumer | 4–5 wks | Planned | bar: Q2 2026 Jun
23 | Consumer | XYZ COMPANY | Validate user experience and customer support | Consumer | 4–5 wks | Planned | bar: Q3 2026 Jul
24 | Consumer | XYZ COMPANY | Redesign pricing structure | Consumer | 5–6 wks | Planned | bar: Q2 2026 Apr to Q4 2026 Dec
25 | Consumer | XYZ COMPANY | Analyize customer behaviour | Consumer | 1-2 months | Planned | bar: Q2 2026 Apr to Q4 2026 Dec
26 | Consumer | XYZ COMPANY | KYC flow & conversion improvement | Consumer | 4–5 wks | Planned | bar: Q3 2026 Jul to Q3 2026 Aug
27 | Consumer | XYZ COMPANY | Payment journey improvements | Consumer | 3–4 wks | Planned | bar: Q2 2026 Jun to Q3 2026 Aug
28 | Consumer | XYZ COMPANY | Cashback & engagement features | Consumer | 3–5 wks | Planned | bar: Q4 2026 Nov to Q4 2026 Dec
29 | Consumer | XYZ COMPANY | Personal finance tools | Consumer | 4–6 wks | Planned | bar: Q3 2026 Sep to Q4 2026 Oct
30 | Consumer | XYZ COMPANY | Loans, BNPL, credit cards | Consumer | 6–8 wks | Planned | bar: Q3 2026 Sep to Q4 2026 Oct
31 | Consumer | XYZ COMPANY | Salary-based account offering | Consumer | 4–5 wks | Planned | bar: Q4 2026 Oct
32 | Consumer | XYZ COMPANY | Non-resident onboarding | Consumer | 5–6 wks | Planned | bar: Q4 2026 Nov
LEGEND
█ Consumer Initiative |  |  |  |  | █ Business Initiative |  | Q3 2026 Sep: █ Q1 Spillover

## Why This Timeline.
XYZ COMPANY · WHY THIS TIMELINE? — Initiative Justification & Analysis
Explains why each roadmap initiative requires its estimated timeline — covering technical complexity, dependencies, and key risks
# | INITIATIVE | SWIMLANE | QUARTER | EST. TIME | COMPLEXITY | WHY THIS TIMELINE? — Technical & Regulatory Rationale | KEY DEPENDENCIES
▶ BUSINESS INITIATIVES
5 | XYZ COMPANY | Business | Q2 – May/Jun | 4–6 wks | HIGH | Complete re-architecture of business onboarding, including KYB KYC, OCR , and AML/CTF controls. Timeline driven by compliance approvals, full requirement finalization, ASC development cycle, and structured UAT across pre-staging, staging, and production before go-live. | • Compliance & MLRO approval on KYB/AML rules • ASC development capacity and timelines • Finalised product & technical requirements • Testing environments readiness (pre-staging, staging, production)
6 | XYZ COMPANY | Business | Q2 – May | 4–5 wks | HIGH | Systematic validation of all branches in the onboarding decision tree, including 50+ test scenarios (rejected documents, partial KYB, sanctions hits). Includes API contract validation and penetration testing on data submission endpoints. Ensures all onboarding, KYC, and KYB flows are error-free and compliant. | • Finalised onboarding/KYC/KYB decision tree • Access to environments (Production) • Development team support for bug fixes
7 | XYZ COMPANY | Business | Q2 – Jun | 4–5 wks | HIGH | Validates all payment corridors, testing failure modes (insufficient funds, declined, timeout, duplicates) and reconciliation accuracy. Starts in June as payment build completes in May. Ensures backend logic, front-end implementation, and API endpoints are fully tested. | • Completed payment (May) • Access to Production environments • Test payment accounts and corridors • Development support for bug fixes • API and backend service readiness • Monitoring/reconciliation
14 | XYZ COMPANY | Business | Q2 – May/Jun/Jul | 2–3 months | HIGH | Issuance of physical and virtual business debit/prepaid cards. Includes requirement gathering, design, approval, development, UAT, and go-live. Full backend infrastructure setup, fraud rule engine configuration, and 3DS authentication setup. | • Approved card requirements and design • ASC/development resource availability • Fraud rules and 3DS configuration • Testing environments for UAT • Internal stakeholder alignment (Product, Compliance, Ops)
16 | XYZ COMPANY | Business | Q2 – May/Jun | 1–2 months | MEDIUM | Starts with event mapping across consumer and business apps, followed by development, testing, and continuous monitoring. Focus on validating funnels, drop-offs, and feature usage to ensure data accuracy and product insights. | • Finalised event tracking plan (consumer & business journeys) • Analytics integration readiness • Development support for instrumentation • Access to test environments for validation • Data accuracy and QA validation • Dashboard/reporting setup • Stakeholder alignment (Product, Data, Engineering)
17 | XYZ COMPANY | Business | Q2 – May | 2–3 wks | MEDIUM | Enables onboarding of multi-director companies onto the ACE Business account. Requires handling multiple stakeholders, KYB verification for all directors, approval workflow , followed by development, UAT, and controlled go-live. | • Defined multi-director onboarding flow & approval logic • KYB/KYC verification for multiple directors • Compliance & MLRO approval • Backend support • Third-party verification providers • Testing environments (pre-staging, staging) • Stakeholder alignment (Product, Compliance, Engineering)
▶ CONSUMER INITIATIVES
21 | XYZ COMPANY | Consumer | Q2 – May | 4–5 wks | HIGH | Systematic validation of all branches in the onboarding decision tree, including 50+ test scenarios (rejected documents, partial KYB, sanctions hits). Includes API contract validation and penetration testing on data submission endpoints. Ensures all onboarding, KYC, and KYB flows are error-free and compliant. | • Finalised onboarding/KYC/KYB decision tree • Access to environments (Production) • Development team support for bug fixes
22 | XYZ COMPANY | Consumer | Q2 – Jun | 4–5 wks | HIGH | Validates all payment corridors, testing failure modes (insufficient funds, declined, timeout, duplicates) and reconciliation accuracy. Starts in June as payment build completes in May. Ensures backend logic, front-end implementation, and API endpoints are fully tested. | • Completed payment (May) • Access to Production environments • Test payment accounts and corridors • Development support for bug fixes • API and backend service readiness • Monitoring/reconciliation
25 | XYZ COMPANY | Consumer | Q2 – May/Jun | 1–2 months | MEDIUM | Starts with event mapping across consumer and business apps, followed by development, testing, and continuous monitoring. Focus on validating funnels, drop-offs, and feature usage to ensure data accuracy and product insights. | • Finalised event tracking plan (consumer & business journeys) • Analytics integration readiness • Development support for instrumentation • Access to test environments for validation • Data accuracy and QA validation • Dashboard/reporting setup • Stakeholder alignment (Product, Data, Engineering)
27 | XYZ COMPANY | Consumer | Q2/Q3 – Jun/Jul | 3–4 wks | MEDIUM | Redesign of the payment journey to enable real-time status updates, improved user experience, and clearer transaction visibility. Includes frontend changes, API enhancements, and frontend updates, followed by testing and controlled rollout. | • Finalised transaction flow design (UX + backend logic) • API and real-time status infrastructure readiness • Integration with payment rails/systems • Development capacity (ASC) • Testing environments (pre-staging, staging) • Monitoring and logging setup • Stakeholder alignment (Product, Engineering, Compliance)
COMPLEXITY LEGEND
HIGH | Significant regulatory, technical, or integration complexity… |  | MEDIUM | Moderate complexity. Some external dependencies or complianc…